## Task List
|  | Fans | Front Office |  | Coaches |  | Regular Line-Up | [5 empty] | Special Teams
| Project Task | Business Users | Business Sponsor / Business Driver | DW/BI Director / Program Manager | Project Manager | Business Project Lead | Business Analyst | Data Steward / QA Analyst | Data Architect / Data Modeler / DBA | Metadata Manager | ETL Architect / ETL Developer | BI Architect / App Developer / Portal Developer | Technical Architect / Tech Support Specialist | Security Manager | Lead Tester | Data Mining / Stats Specialist | Educator
PROJECT/PROGRAM LAUNCH AND MANAGEMENT | [17 empty] | LEGEND:
| PROJECT DEFINITION | [16 empty] | l | Primary responsibility
1 | Assess DW/BI readiness |  | m | m | l | l | t |  | t | [8 empty] | m | Involved
2 | Develop preliminary project scope/charter |  | m | m | l | l | t |  | t |  | t | t | t |  |  |  |  | t | Provides input
3 | Build business justification | t | m | t | l | l | t |  | t |  | t | t | t |  |  |  |  | r | Informed of results
PROJECT PLANNING & MANAGEMENT
1 | Establish project identity |  | t | t | l | l
2 | Identify project resources |  |  | t | l | l
3 | Prepare project plan |  | r | r | l | l | m | m | m | m | m | m | m | m | m | m | m
4 | Develop project communication plan |  | t | t | l | l
5 | Conduct project team kick-off & planning |  | t | t | l | l | m | m | m | m | m | m | m | m | m | m | m
6 | Develop process to manage scope/control changes |  | t | t | l | l
7 | Develop process to measure success |  | m | t | l | l
8 | User acceptance/project review | r | m | m | l | l | m | r | r | r | r | r | r | r | r | r | r
9 | Ongoing project management | r | r | r | l | l | m | m | m | m | m | m | m | m | m | m | m
PROGRAM PLANNING & MANAGEMENT
1 | Establish governance responsibility/process | r | m | l | m | m | r | r | r | r | r | r | r | r | r | r | r
2 | Establish program communication plan |  | m | l | m | m
3 | Establish enterprise data stewardship |  | r | l | m | m |  | m | m | m | m
4 | Establish program best practices |  |  | l | m | m | m | m | m | m | m | m | m | m | m | m | m
5 | Conduct periodic program assessments | t | m | l | m | m | m | m | m | m | m | m | m | m | m | m | m
6 | Ongoing program management | r | r | l | m | m | r | r | r | r | r | r | r | r | r | r | r
BUSINESS REQUIREMENTS DEFINITION
1 | Identify and prepare interview team |  |  |  | l | m | m
2 | Select interviewees |  | t | t | l | l | m | t |  |  |  | t
3 | Schedule interviews |  |  |  | l | l | l
4 | Prepare interview questionnaires |  |  |  | m | m | l | t | t |  | t | t | t |  |  | t
5 | Conduct user kick-off & prepare interviewees | m | m | m | l | l | m | t | t |  | t | t | t |  |  | m
6 | Conduct business user interviews | m | m | m | m | m | l |  | m |  | m | m |  |  |  | m
7 | Conduct IT data audit interviews |  |  |  | m |  | l | m | m |  | m | m
8 | Publish interview write-ups and incorporate feedback. | r |  |  | m | r | l |  | r |  | r | r
9 | Analyze interview findings |  |  |  | m | m | l | m | m |  | m | m
10 | Document findings and review |  | t | t | m | m | l
11 | Publish requirements deliverables | r | r | r | m | m | l | r | r | r | r | r | r | r | r | r | r
12 | Prioritize and revise project scope | t | m | m | l | l | m |  | t |  | t | t | t
13 | User acceptance/project review | r | m | m | l | l | m | r | r | r | r | r | r | r | r | r | r
DW/BI TECHNICAL ARCHITECTURE
APPLICATION ARCHITECTURE DESIGN
1 | Create architecture task force |  |  |  | m | m | [6 empty] | l
2 | Gather & document technical requirements | [11 empty] | l
3 | Review current technical environment |  |  |  | m |  | m |  | m |  | m | m | l
4 | Develop architecture implications document | [5 empty] | m |  | m |  | m | m | l
5 | Create architecture model | [5 empty] | t |  | m |  | m | m | l
6 | Determine phased implementation approach |  |  |  | m | m | [6 empty] | l
7 | Define and specify subsystems | [7 empty] | m |  | m | m | l
8 | Create the architecture plan | [7 empty] | t |  | t | t | l
9 | Develop configuration recommendations | [7 empty] | t |  | t | t | l
10 | User acceptance/project review | r | r | r | l | m | r | r | r | r | r | r | m | r | r | r | r
PRODUCT SELECTION
(Repeat for each selection area)
1 | Develop evaluation matrix |  |  |  | l | l | m |  | m |  |  |  | l
2 | Research candidate products |  |  |  | m |  | m |  | m |  |  | m | l
3 | Develop product short list |  |  |  | m |  | m |  | m |  |  | m | l
4 | Evaluate product options | t |  |  | m | m | m |  | m |  |  | m | l
5 | Optional prototype (may repeat for multi products)
| Select business process / data for evaluation |  |  |  | l | l | m |  | m
| Define completion criteria |  |  |  | l | l | [6 empty] | m
| Acquire resources (internal/vendor) |  |  |  | l | m
| Determine test configuration |  |  |  | m |  |  |  | m |  |  | m | l
| Install evaluation prerequisites & components | [5 empty] | m |  | m |  |  | m | l
| Train the evaluation team | m |  |  | l | m | m |  | m |  |  | m | m |  |  |  | m
| Develop & tune prototype |  |  |  | m |  | m |  | l |  |  | l | l
| Conduct tests | t |  |  | t | t | t |  | l |  |  | l | l |  |  |  | t
| Analyze & document results | t |  |  | l | m | t |  | t |  |  | t | l
6 | Determine product recommendation | t | r | r | l | l | m |  | m |  |  | m | l
7 | Present findings/results to management |  | r | r | l | l | t
8 | Enter trial phase | m |  |  | l |  | m |  |  | m | m | m | m | m
9 | Negotiate contract |  | m | m | l
10 | User acceptance/project review | r | r | r | m | l | m | r | m | r | r | m | m | r | r | r | m
MANAGE METADATA
1 | Inventory metadata elements, locations, and relationships | m |  |  | m | m | m | m | m | l | m | m | m | m |  | m | m
2 | Educate team on metadata situation and responsibilities | m |  |  | m | m | m | m | m | l | m | m | m | m |  | m
3 | Identify key elements to manage | m |  |  | m | m |  | m |  | l
4 | Create systems to capture additional metadata | [7 empty] | m | l |  | m
5 | Create tools to synchronize metadata | [8 empty] | l |  | m
6 | Design and implement metadata delivery system | [7 empty] | m | l |  | m
7 | Document metadata strategy |  |  |  | m |  |  |  |  | l
8 | Ongoing metadata management and monitoring | [8 empty] | l
9 | User acceptance/project review | r | r | r | l | m | r | r | r | l | r | r | m | r | r | r | r
IMPLEMENT TACTICAL SECURITY MEASURES
1 | Develop tactical security plan |  |  |  | m | m | [6 empty] | m | l
2 | Secure physical environment |  |  |  | m | [7 empty] | l | m
3 | Secure access into environment |  |  |  | m | [7 empty] | l | l
4 | Secure access out of environment |  |  |  | m | [7 empty] | l | l
5 | Implement rigorous password scheme |  |  |  | m | [7 empty] | l | l
6 | Implement controls for software installation |  |  |  | m | [7 empty] | l | m
7 | Audit security violations |  |  |  | m | m | [6 empty] | l | l
8 | Monitor security privileges by individual |  |  |  | l | m | [6 empty] | m | m
9 | User acceptance/project review | r | r | r | l | m | r | r | r | r | r | r | m | m | r | r | r
DEVELOP STRATEGIC SECURITY PLAN
1 | Design security architecture |  |  |  | m | [7 empty] | m | l
2 | Implement access services |  |  |  | m | [7 empty] | m | l
3 | Implement authentication services |  |  |  | m | [7 empty] | m | l
4 | Implement external access services |  |  |  | m | [7 empty] | m | l
5 | Centralize authentication and access control |  |  |  | m | [7 empty] | m | l
6 | Implement security monitoring and compliance sys |  |  |  | m | [7 empty] | m | l
7 | User acceptance/project review | r | r | r | l | m | r | r | r | r | r | r | m | l | r | r | r
CREATE INFRASTRUCTURE PLAN
1 | Create draft infrastructure model and plan |  |  |  | m | [7 empty] | l
2 | Review/update plan with key IT groups |  |  |  | m | [7 empty] | l
3 | Create final version of initial plan |  |  |  | m | [7 empty] | l
4 | Monitor and update plan |  |  |  | m | [7 empty] | l
5 | User acceptance/project review | r | r | r | l | m | r | r | r | r | r | r | m | r | r | r | r
PRODUCT INSTALLATION
(Repeat for each product)
1 | Installation planning | [11 empty] | l
2 | Meet prerequisites | [11 empty] | l
3 | Install hardware / software | [11 empty] | l
4 | Test hardware / software | [11 empty] | l
5 | User acceptance/project review | m | r | r | l | m | m | r | m | r | r | m | m | r | r | r | r
IMPLEMENTATION
DIMENSIONAL DATA MODEL DESIGN
1 | Review business requirements |  |  |  | m | m | l | m | m |  | m | m
2 | Review/develop data warehouse bus matrix | t | t | t | m | t | l | t | l
3 | Select business process | t | m | m | m | l | m |  | m
4 | Declare fact table grain | t |  |  | m | m | m | m | l |  | m | m
5 | Identify dimensions | t |  |  | m | m | m | m | l |  | m | m
6 | Identify metrics | t |  |  | m | m | m | m | l |  | m | m
7 | Develop high level model diagram | t |  |  | m | m | m | m | l |  | m | m
8 | Document attributes list | t |  |  | m | m | m | m | l |  | m | m
9 | Identify candidate data sources | t |  |  | m | m | m | m | l |  | m | m
10 | Profile data |  |  |  | m |  | m | m | l |  | m | m |  |  | r
11 | Develop base and derived metrics | t |  |  | m | m | m | m | l |  | m | m
12 | Design detailed dimensional model | t |  |  | m | m | m | m | l |  | m | m
13 | Review data model with IT |  | r | r | m | m | m | m | l | m | m | m | m | m | m | m | m
14 | Review data model with business users | m | r | r | m | m | m |  | l
15 | Review design recommendations for BI Tool |  |  |  | m |  | m |  | l |  |  | l
16 | Review design recommendations for DBMS |  |  |  | m |  | m |  | l
17 | Finalize logical design documentation |  | r | r | m | r | m | r | l | r | r | r | r | r | r | r | r
18 | Draft source to target data map |  |  |  | m |  | m | m | l | t | l
19 | User acceptance/project review | m | r | m | l | m | m | r | m | r | r | r | r | r | r | r | r
PHYSICAL DATABASE DESIGN
1 | Define standards for physical objects | [7 empty] | l
2 | Design physical tables & columns | [7 empty] | l
3 | Finalize the source to target map |  |  |  | m |  | m | m | l |  | l
4 | Estimate database size |  |  |  | m |  | m |  | l |  | m
5 | Design development database | [7 empty] | l |  | m
6 | Design auditing and staging tables | [7 empty] | m | t | l |  |  |  | r
7 | Develop initial index plan | [5 empty] | t |  | l |  | t | t
8 | Design the OLAP database | [5 empty] | m |  | l |  | t | m | t |  | r
9 | Develop initial aggregation plan | [5 empty] | m |  | l |  |  | t |  |  | r
10 | Develop initial partitioning plan | [7 empty] | l |  | t |  | t
11 | User acceptance/project review |  | r | r | l | r | m | t | m | t | m | m | m | m | r | r | r
PHYSICAL DATABASE IMPLEMENTATION
1 | Install and setup the RDBMS | bar: l m; t m
2 | Build physical storage structure | bar: l m
3 | Implement table partitioning | bar: l m; t m; t m
4 | Complete table and index sizing | bar: l m
5 | Create tables and indexes | bar: l m
6 | Create OLAP database | bar: l m
7 | User acceptance/project review |  | r | r | l | r | m | m | m | r | m | m | m | r | r | r | r
ETL SYSTEM DESIGN
1 | Design high level ETL process |  | l: m; l m: t; t m: l; t m: t
2 | Test, choose and implement an ETL tool | bar: l; l m; t m; t m to t m
3 | Develop default strategies for extracting data |  | l: m; l m: m; t m: l; t m: m; t m: t
4 | Develop default strategies for archiving extracted data | bar: l; l m; t m; t m
5 | Develop default strategies for policing data quality | bar: l; t; t m; t m
6 | Develop default strategies for dimension change mgmt | bar: l; l m; t m; t m
7 | Design strategy to meet availability requirements | bar: l; l m; t m; t m
8 | Design data auditing subsystem | bar: l; t to l m; t m; t m
9 | Design the structure of the ETL staging area | bar: l; l m; t m; t m
10 | Develop plan for maintaining dimension hierarchies |  | l: m; t: m; l m: m; t m: l; t m: t
11 | Design detailed ETL plans for each table |  | l: m; t: m; l m: m; t m: l; t m: t
12 | Set up initial job sequencing |  | l: m; l m: m; t m: l; t m: t
13 | Document the ETL system specification |  | l: m; l m: m; t m: l; t m: t; t r: m
14 | User acceptance/project review |  | r | r | l | m | m | m | m | r | m | m | m | r | m | r | m
ETL SYSTEM DEVELOPMENT
1 | Build dimension table surrogate key mgmt system |  | l: m; l m: m; t m: l; t m: t
2 | Build the audit system or template |  | l: m; l m: m; t m: l; t m: t
3 | Load the date table and other static dimensions |  | l: m; t: m; l m: m; t m: l; t r: t
4 | Build historic loads for type 1 dimension tables; test |  | l: m; t: m; l m: m; t m: l; t r: t
5 | Build historic loads for type 2 dimension tables; test |  | l: m; t: m; l m: m; t m: l; t r: t
6 | Build fact table surrogate key pipeline |  | l: m; l m: m; t m: l; t m: t
7 | Build historic fact table loads; test |  | l: m; t: m; l m: m; t m: l; t r: t
8 | Build dimension attrib incremental change mgmt sys |  | l: m; l m: m; t m: l; t m: t
9 | Build dimension table incremental loads; test |  | l: m; t: m; l m: m; t m: l; t r: t
10 | Build fact table incremental loads; test | bar: l; t to l m; t m; t r
11 | Build agg table load/OLAP cube processing; test | bar: l; t to l m; t m; t r
12 | Design, build and test ETL system automation | bar: l; t to l m; t m; t m; t r
13 | User acceptance/project review |  | r | r | l | m | m | m | m | r | m | m | m | r | m | r | m
BI APPLICATION DESIGN
1 | Create application standards and templates |  | l: m; r: m; m: m; t m: l; t r: m; t r: t
2 | Identify and prioritize candidate applications | t | bar: l to m; l m; t m
3 | Document detailed BI application specifications |  | m: m; t m: l; t r: r
4 | Design navigation framework | t | bar: m; t m
5 | Validate the applications and data model | bar: l to l m; t m; t r
6 | Review BI application specs with business users | m | bar: l to m; l m; t m; t r
7 | Revise BI application specs | bar: m; t m
8 | Develop BI application test plans | bar: l; m to t; t m; t r
9 | User acceptance/project review | m | m | m | l | m | m | r | m | r | r | m | r | r | r | r | r
BI APPLICATION DEVELOPMENT
1 | Review application specifications and standards | t | bar: m; t m
2 | Populate BI tool metadata | bar: m to t; l t; t m
3 | Create business metadata | t | bar: m to t; l t; t m
4 | Test BI tools | bar: l to t; l t; t m to t m
5 | Set up user security |  | l: m; r: t; m: t; t m: l; t m: m
6 | Set up report process metadata system |  | m: t; l t: l; t m: m
7 | Develop BI applications |  | m: m; t: t; l m: m; l t: m; t m: l; t r: m
8 | Validate data model and data | bar: l to l m; t m to t m; t r
9 | Provide data accuracy & cleanliness feedback |  | l: m; r: t; m: t; t: l; l m: t; t m: m; t m: m; t r: t
10 | Develop BI portal | bar: m; t m
11 | Set up report execution scheduling | bar: l to m; t m
12 | Test BI applications and verify data | bar: l to l m; t m to t m; t r
13 | Document BI applications | bar: r to t; l t; t m
14 | Develop BI application maintenance procedures | bar: l; m to t; t m
15 | Develop BI application deployment procedures | bar: l to m; l m to l t; t m
16 | User review/project acceptance | m | r | r | m | m | m | m | m | m | m | l | r | r | r | r | r
DEPLOYMENT & OPERATIONS
Pre-Deployment Testing
1 | Develop a plan for implementing testing |  | r: t; l: m; t: m; l m: m; t m: m; t m: m; t r: l
2 | Purchase and implement test management tools | bar: t to l m; t m; t r
3 | Develop test datasets | bar: t to l m; t m; t r
4 | Define tests | bar: t to l m; t m; t r
5 | User acceptance/project review | r | r | r | l | m | m | m | m | r | m | r | m | r | m | r | m
Data and Process Testing
1 | Test historic load | m | bar: l to r; t to l m; t m; t r
2 | Test primary dataset for incremental load | bar: l to r; t to l m; t m; t r
3 | Conduct live tests with real data | m | bar: l to r; t to l m; t m; t r
4 | Test overall process and system integration | bar: l to r; t to l m; t m; t r
5 | Test month-end or other unusual conditions | m | bar: l to r; t to l m; t m; t r
6 | User acceptance/project review | r | m | r | l | m | m | m | m |  | m | m | m |  | m |  | m
Performance Tuning
1 | Test conformance to Service Level Agreements | bar: l to r; t to l m; t m to t m; t r
2 | Test performance of data loads | bar: l; l m; t m; t m; t r
3 | Improve performance of data loads | bar: l; l m; t m; t m
4 | Test query performance | bar: l to m; l m; t m to t m; t r
5 | Improve query performance via new indexes and/or aggregations | bar: l; m; l m; t m to t m
6 | End-to-end testing of system after performance-related changes | bar: l to l m; t m to t m; t r
7 | User acceptance/project review | r | m | r | l | m | m | m | m | r | m | m | m | r | m | r | r
Other Testing
1 | Usability testing of BI applications and portal | m | bar: l to m; t m
2 | Confirm desktop readiness | m | bar: l; t m to t m
3 | User acceptance/project review | r | r | r | m | l | m | m | m |  | m | m | m |  |  |  | m
System Deployment
1 | Develop playbook for relational DW deployment | bar: l to r; t to l t; t m to t m
2 | Develop playbook for ETL system deployment | bar: l to r; t to t m; t m to t m
3 | Develop playbook for OLAP database deployment | bar: l to r; t to l t; t m to t m
4 | Develop playbook for BI application deployment | bar: l to r; t to l t; t m to t m; t r
5 | Deploy new or changed system | bar: l to r; t to l m; t m
6 | User acceptance/project review | r | m | r | m | l | m | m | m |  | m | m | m |  |  |  | m
User Facing Deployment
1 | Develop documentation |  |  |  | m | m | m | m | t | m |  | m | m | t |  | m | l
2 | Develop training |  |  |  | m | m | m | m | t | m |  | m | m | t |  | m | l
3 | Deliver training | m |  |  | m | m | m | t | t | t | t | t | m | t |  | t | l
4 | User acceptance/project review | r | r | r | m | l | m | m | m | t | m | m | m | r |  | t | m
Back Room Operations
1 | Develop back roomoperations plan | bar: m; m
2 | Maintain physical database and disks | bar: m
3 | Maintain indexes and partitions | bar: m
4 | Perform regular backups and test recovery | bar: m
Front Room Operations
1 | Develop support plan | bar: r to m; m
2 | Ongoing BI portal maintenance | bar: r; m; m to m
3 | Ongoing user guidance for developing queries and reports | r: t; m: m; m: m; m: l
4 | Ongoing standard report development | r: t; m: m; m: l; m: t